## Sheet1
Stages
Staff
| Planning | Designing | Developing | Testing |  | Implementing | Total
| (2 weeks) | (3 weeks) | (3 weeks) | (1 week) |  | (1 week) | Time
Project Manager | 50.0 hours * | 55.0 hours * | 50.0 hours * | 45.0 hours * |  | 40.0 hours * | 500 hours
| 2week | 3weeks | 3weeks | 1week |  | 1week
Instructional Designer | 40.0 hours * | 40.0 hours * | 45.0 hours * | 40.0 hours * |  | 40.0 hours * | 410 hours
| 2week | 3weeks | 3weeks | 1week |  | 1week
Subject Matter Expert |  | 40.0 hours * |  |  |  |  | 120 hours
3weeks
Graphic Designer |  | 40.0 hours * | 50.0 hours * | 50.0 hours * |  | 40.0 hours * | 360 hours
|  | 3weeks | 3weeks | 1 week |  | 1 week
System Programmer |  | 40.0 hours * | 45.0 hours * | 50.0 hours * |  | 40.0 hours * | 300 hours
|  | 2weeks | 3weeks | 1week |  | 1week
Writer/Editor |  | 45.0 hours * | 50.0 hours |  | * |  | 140 hours
|  | 2weeks |  | 1week
Reviewer |  | 40.0 hours |  | 40.0 hours * |  |  | 40 hours
1week
Total Time | 90 hours | 695 hours | 615 hours | 225 hours |  | 160 hours | 1785 hours